## Sheet1
EENG 4640 Capstone Senior Project Schedule
Project Name | Obstacle-Aware Trajectory Replanning of Robotic Arm |  |  |  | Start Date |  |  | Project Duration
[5 empty] | year | 2026 |  | No. of Days | 107
Approved By | Dr. Mingyu Kim |  |  |  | month | 1 |  | No. of Weeks | 15.2857
[5 empty] | day | 16 |  | Work Days | 76
Design Team | Names
Team Leader | Sebastian Oviedo |  |  |  | End Date
Project Designer 1 | Elizabeth McGlone |  |  |  | year | 2026
Project Designer 2 | Ariana Story |  |  |  | month | 5
Project Designer3 | Anish Goyal |  |  |  | day | 3
[10 empty] | ✔️ | Week 1 | 1/12-1/18
[10 empty] | ✔️ | Week 2 | 1/19-1/25 |  |  |  | 70
|  | Tasks | Start Week | Duration in Weeks | [5 empty] | ✔️ | Week 3 | 1/26-2/1
[10 empty] | ✔️ | Week 4 | 2/2-2/8 | Research abstract & Formal proposal | 0 | #REF!
[10 empty] | ✔️ | Week 5 | 2/9-2/15 | Intent to Present | #REF!
|  | Decide on project idea | 1 | 1 | [5 empty] | ✔️ | Week 6 | 2/16-2/22 |  | #REF!
|  | Literature review | 1 | 4 | [6 empty] | Week 7 | 2/23-3/1
|  | Research components | 1 | 3 | [6 empty] | Week 8 | 3/2-3/8 | Midterm presentation & Poster Submission | 2
|  | Software & hardware block diagrams | 2 | 2 | [6 empty] | Week 9 | 3/9-3/15 |  | #REF!
|  | CAD review / modification (arm scaling + mounts) | 3 | 4 | [6 empty] | Week 10 | 3/16-3/22 | Spring Break
|  | Abstract | 3 | 1 | [6 empty] | Week 11 | 3/23-3/29 | Poster Demonstrations (Symposium)
|  | Formal project proposal | 4 | 1 | [6 empty] | Week 12 | 3/30-4/5
|  | Order parts (Braccio, sensors, electronics) | 4 | 2 | [6 empty] | Week 13 | 4/6-4/12 | Webpage demponstrations
|  | Power system assembly & decoupling PCB | 6 | 3
|  | Sensor mounting (ToF + IR redesign & print) | 6 | 3
|  | Midterm presentation | 7 | 1
|  | Software development (base IK control) | 5 | 5
|  | Software development (reactive control using ToF/IR) | 8 | 4
|  | MATLAB robotics simulation & validation | 8 | 4
|  | System integration (arm + sensors + control) | 9 | 4
|  | Initial testing | 11 | 2
|  | Adjustments & debugging | 12 | 2
|  | Full system testing | 13 | 2
|  | Sustainability presentation | 12 | 1
|  | Poster demonstration | 13 | 1
|  | System validation | 13 | 2
|  | Optimization & refinement | 14 | 2
|  | Project technically complete | 14 | 1
|  | Comprehensive report | 13 | 3
|  | Webpage demonstration (GitHub + documentation) | 6 | 8
|  | Demo preparation & buffer | 14 | 2
|  | Formal project presentation | 15 | 1
|  | Final demo & project completion | 16 | 1
|  | Start |  |  |  |  | End
|  | 2026-01-16 |  |  |  |  | 2026-05-03
Gantt Chart
46145
46038