## Sheet1
Spring Semester Schedule
Week 1 |  | Week 2 | Week 3 | Week 4 | Week 5 |  | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Sebastian | Parts selection, initial/formal proposal, and task allocation/literature review |  |  |  | Robot Arm Acquisition and Tuning, PCB design for sensor & teensy housing |  | Robot Arm Acquisition and Tuning, PCB design for sensor & teensy housing | MCU Soldering, sensor testing | MUXing the I2C ToF sensors. Developing algorithm to read from each sensor periodically.
Anish |  |  |  |  | Review IK Github for Arduino Braccio |  | Review IK Github for Arduino Braccio, start development on movement/speed control software with post processing waveforms of joint states
Elizabeth |  |  |  |  | CAD Mounting Brackets for Sensor Array |  | CAD Mounting Brackets for Sensor Array
Ariana |  |  |  |  | CAD Mounting Brackets for Sensor Array |  | CAD Mounting Brackets for Sensor Array
Complete
In Progress
Not started
Task List
|  |  | TASK DESCRIPTION |  |  | PRIORITY
|  |  | Mount Sensor Array on Robotic Arm |  |  | HIGH
|  |  | Develop comprehensive IK-based controller for arm that allows speed control while maintaining precision |  |  | HIGH
|  |  | Model obstacle sensing in IK-based controller using ToF sensors |  |  | HIGH
|  |  | Program second layer (IR) sensor using hysteresis filter |  |  | HIGH
|  |  | Use sensor model as a simple obstacle to avoid in the IK inertial space |  |  | HIGH
|  |  | Design a demo circuit showing all the sensors, cable routing, MCUs, and PSUs |  |  | HIGH
|  |  | Integrate trajectory optimization problem as a convexified program with nonlinear global solver, as well as linear relaxation that enables online trajectory computations |  |  | MEDIUM
|  |  | Come up with more interactive default task for the robotic arm |  |  | LOW